## Aircraft Tracker
Tail Number | Aircraft Type | Part 135 Flying? | W&B Date | W&B on Jet Insight | ForeFlight W&B Built | Starlink on W&B? | Initial ForeFlight Build | ForeFlight Subscription | ForeFlight Config Built | Validation Complete | Beta Tested | Go-Live Approved | Genesis Removed | Overall Status | Notes
N520FX | Challenger 300 | NO | Asked Noah | NO | No | Unsure | Yes | Yes | No | No | No | No | No | Not Started | Awaiting Starlink Install. | Standard Rafts are two in the Galley
N541FX | Challenger 300 | NO |  |  |  |  | Yes | No
N533FX | Challenger 300 | NO |  |  |  |  | Yes | No
N526FX | Challenger 300 | NO |  |  |  |  | Yes | No | [5 empty] | Not Started
N548FX | Challenger 300 | NO |  |  | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Configured
N555FX | Challenger 300 | NO |  |  | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Configured
N554FX | Challenger 300 | Starts flying Wednesday | 2026-01-20 |  | yes | Yes | Yes | Yes | Yes
N521FX | Challenger 300 | YES | 2025-11-24 | NO | Yes | Unsure | Yes | Yes | Yes | No | No | No | No | Configured | Awaiting Starlink Install.
N371BD | Challenger 300 | YES | 2025-11-17 | 522 is attached to 371 | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured | PDC is turned off, why?
N883TR | Challenger 300 | YES | 2025-11-19 | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | Configured | Awaiting Starlink Install.
N416F | Challenger 300 | YES | 2025-12-12 | YES | Yes | Unsure | Yes | Yes | Yes | No | No | No | No | Configured | Couch (2 lift rafts by couch and one galley)
N519FX | Challenger 300 | YES | 2025-11-20 | NO | Yes | Unsure | Yes | Yes | Yes | No | No | No | No | Configured | Awaiting Starlink Install.
N552FX | Challenger 300 | YES | 2026-01-10 | NO | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N553FX | Challenger 300 | YES | 2026-01-25 | NO | Yes | YES | Yes | Yes | No | No | No | No | No | Not Started
N992MG | Cessna Citation X | YES | 2025-05-07 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N513JB | Cessna Citation X | YES | 2025-10-02 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N957JS | Cessna Citation X | YES | 2025-10-10 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N954JS | Cessna Citation X | YES | 2025-09-10 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N860TX | Cessna Citation X | YES | 2025-05-25 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N700LH | Cessna Citation X | YES | 2025-06-03 | YES | Yes | YES | Yes | Yes | Yes | Yes | No | No | No | Validated
N106PC | Cessna Citation X | YES | 2025-05-05 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N818CF | Cessna Citation X | YES | 2025-04-03 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N733FL | Cessna Citation X | YES | 2025-06-09 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N988TX | Cessna Citation X | YES | 2025-06-22 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N703TX | Cessna Citation X | YES | 2025-05-07 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N910E | Cessna Citation X | YES | 2025-09-12 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N102VR | Cessna Citation X | YES | 2025-07-03 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N998CX | Cessna Citation X | YES | 2025-07-14 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N51GB | Cessna Citation X | YES | 2025-10-14 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N939TX | Cessna Citation X | YES | 2025-08-22 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N301HR | Cessna Citation X | YES | 2025-08-14 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N971JS | Cessna Citation X | YES | 2025-07-22 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N125DZ | Cessna Citation X | YES | 2025-09-06 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N955GH | Cessna Citation X | YES | 2025-08-31 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N125TH | Cessna Citation X | YES | 2025-04-04 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured
N201HR | Cessna Citation X | YES | 2025-08-29 | YES | Yes | YES | Yes | Yes | Yes | No | No | No | No | Configured

## Sheet1
KOW533 | N533FX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/6c27bdb0-e1c7-42fc-b7d9-e290b630ea0e.ics
KOW519 | N519FX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/1fdfb34f-df94-45cb-ab8f-c3f0e129e080.ics
KOW541 | N541FX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/d82f2424-7fd4-4063-86f0-b057a25a8292.ics
KOW521 | N521FX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/96a0059c-3d27-43dd-84f5-fb6c8cacf0b3.ics
KOW554 | N554FX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/d1f25f15-f4ba-4b77-af64-815eda3076f2.ics
KOW992 | N992MG | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/d974ac0b-676f-4f8c-950f-07e9adf05bdd.ics
KOW988 | N988TX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/9d82991f-f1e7-419f-82d1-654e43b6c35e.ics
KOW733 | N733FL | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/ab0cbcd9-b8d6-4d73-9018-1a676edc0b1d.ics
KOW883 | N883TR | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/fcf890fc-79eb-4690-af97-8c3fc8324142.ics
KOW519 | N519FX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/f38d8ea0-8548-48b1-a5ee-9fbcafab508b.ics
KOW416 | N416F | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/3b2a32f7-ce7d-4ba2-a77d-e4ade338c1cd.ics
KOW954 | N954JS | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/2e774935-4ed3-46bb-b063-0b141b81f75b.ics
KOW939 | N939TX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/02fb0ab3-1653-4120-b0cd-1a9b6f4dc79b.ics
KOW998 | N998CX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/16ca7cce-55ab-4898-a4a2-638c21d64b3f.ics
KOW971 | N971JS | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/651d5f51-c00a-46f2-9a61-28656cd8b4f9.ics
KOW51 | N51GB | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/cd9e6d92-9c0b-4cdd-93d0-71d536606dab.ics
KOW513 | N513JB | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/e3e56cc5-02b7-40f4-8364-5dd107b88f9b.ics
KOW201 | N201HR | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/ae8aadc9-345f-46f6-a35a-2bbff73c52e2.ics
KOW910 | N910E | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/1aeaeb43-8a8a-4fdd-8370-9e25d70c5259.ics
KOW106 | N106PC | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/a4af0f1e-91ce-4c62-be5b-3a5abfc40df1.ics
KOW860 | N860TX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/61a9444f-391c-4d1b-b31a-c674bf8cb31d.ics
KOW301 | N301HR | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/8d85c3ca-1b0c-4e07-9e66-659d45eeb36a.ics
KOW102 | N102VR | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/ad189512-55ab-44a4-9650-49585d396e39.ics
KOW700 | N700LH | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/3018385e-47a1-494f-9529-28ece1d00265.ics
KOW957 | N957JS | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/2c0109c1-8c89-493f-96ec-622d5d666edd.ics
KOW703 | N703TX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/8e3bc5e7-1404-4155-967c-1c9fd938928d.ics
KOW187 | N187CR | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/d73abfe9-8897-4495-a561-b4bb5cb679bd.ics
KOW125 | N125TH | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/e0d27c6b-f948-46c1-9e47-73db3d2e3b5e.ics
KOW25 | N125DZ | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/f868be07-b53c-423c-ba48-34145f151fd1.ics
KOW818 | N818CF | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/e9ff5824-3fa5-4257-872c-1913289c6e4f.ics
KOW955 | N955GH | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/101f1de2-152a-4526-97c7-6c4960429e8a.ics
KOW552 | N552FX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/53edb02e-55d4-4ea6-a148-1e9eb85a96c9.ics
KOW553 | N553FX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/093bca25-a354-40c1-86ef-66fc24a88ad6.ics
KOW371 | N371DB | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/30f1f4c4-fd05-4132-a467-fb96f2a0a4ac.ics
KOW520 | N520FX | https://portal.jetinsight.com/schedule/00256885-a3f2-4df8-977d-961dbb677778/14e93c55-5d85-4ce3-9d8d-49d177e1c989.ics